## Feature Matrix
POWER PLATFORM FEATURE PRIORITIZATION MATRIX
Edit blue 1–10 score cells and the Scoring Weights sheet. Rankings, tiers, and RICE recalculate automatically in Excel.
ID | Category | Feature | Target Phase | Market Demand | Revenue Potential | SEO Value | Differentiation | Effort Efficiency | Weighted Score | Rank | Priority Tier | Confidence | Reach | Impact | Effort | RICE Score | Recommended Model | Strategic Rationale | Owner | Status | Notes
1 | Power Apps | Power Apps Component Library | MVP | 10 | 9 | 9 | 9 | 8 |  |  |  | 9 | 10 | 10 | 3 |  | Freemium + Pro | Core acquisition wedge; reusable production UI assets |  | Backlog
2 | Power Apps | Power Apps YAML Exporter | MVP | 10 | 9 | 8 | 10 | 7 |  |  |  | 8 | 9 | 10 | 4 |  | Pro subscription | Converts discovery into immediate maker productivity |  | Backlog
3 | Power Apps | Responsive Layout Library | MVP | 10 | 8 | 9 | 8 | 9 |  |  |  | 9 | 10 | 9 | 2 |  | Freemium | Common implementation pain with fast time to value |  | Backlog
4 | Power Apps | Enterprise Design System | Growth | 9 | 10 | 7 | 10 | 5 |  |  |  | 8 | 8 | 10 | 7 |  | Enterprise license | High-value standardization for consulting and enterprises |  | Backlog
5 | Power Apps | Government UX Toolkit | Growth | 8 | 10 | 6 | 10 | 6 |  |  |  | 8 | 6 | 10 | 6 |  | Pack + enterprise | Defensible public-sector accessibility niche |  | Backlog
6 | Power Apps | Accessibility Template Pack | MVP | 9 | 9 | 8 | 9 | 8 |  |  |  | 9 | 8 | 9 | 3 |  | Premium pack | Practical compliance accelerator |  | Backlog
7 | Power Apps | Canvas App Template Marketplace | MVP | 9 | 9 | 9 | 8 | 7 |  |  |  | 8 | 9 | 9 | 5 |  | Marketplace commission | Broad marketplace entry point |  | Backlog
8 | Power Apps | Form Template Library | MVP | 9 | 8 | 9 | 7 | 9 |  |  |  | 9 | 9 | 8 | 2 |  | Freemium | High-frequency maker need |  | Backlog
9 | Power Apps | Dashboard Screen Templates | MVP | 9 | 8 | 8 | 8 | 9 |  |  |  | 9 | 8 | 8 | 2 |  | Premium pack | Visual acquisition and bundle potential |  | Backlog
10 | Power Apps | PCF Control Marketplace | Scale | 9 | 10 | 8 | 8 | 4 |  |  |  | 7 | 8 | 10 | 9 |  | Marketplace commission | Higher technical value but support-heavy |  | Backlog
11 | Power Apps | Theme and Palette Generator | MVP | 10 | 8 | 10 | 8 | 9 |  |  |  | 9 | 10 | 8 | 2 |  | Freemium + sponsorship | SEO-friendly free tool and lead magnet |  | Backlog
12 | Power Apps | Component AI Configurator | Growth | 9 | 9 | 8 | 10 | 5 |  |  |  | 7 | 8 | 9 | 8 |  | Pro subscription | Strong differentiation with export upsell |  | Backlog
13 | Power Automate | Flow Expression Builder | MVP | 10 | 8 | 10 | 8 | 9 |  |  |  | 9 | 10 | 8 | 2 |  | Freemium | High-volume search intent and low build effort |  | Backlog
14 | Power Automate | Error Handling Framework | MVP | 10 | 9 | 9 | 9 | 8 |  |  |  | 9 | 9 | 10 | 3 |  | Premium pack | Production reliability pain |  | Backlog
15 | Power Automate | Reusable Child Flow Framework | MVP | 9 | 9 | 8 | 9 | 7 |  |  |  | 9 | 8 | 10 | 4 |  | Premium pack | Enterprise pattern with strong bundle value |  | Backlog
16 | Power Automate | Approval Workflow Framework | Growth | 9 | 10 | 8 | 9 | 6 |  |  |  | 8 | 8 | 10 | 6 |  | Pack + consulting | Large enterprise use-case breadth |  | Backlog
17 | Power Automate | Logging and Telemetry Framework | Growth | 9 | 10 | 7 | 9 | 6 |  |  |  | 8 | 7 | 10 | 6 |  | Enterprise license | Supports production operations |  | Backlog
18 | Power Automate | Flow Monitoring Dashboard | Growth | 9 | 10 | 8 | 9 | 5 |  |  |  | 8 | 8 | 10 | 7 |  | Subscription | Recurring operational need |  | Backlog
19 | Power Automate | Secure API Integration Patterns | Growth | 8 | 10 | 7 | 10 | 6 |  |  |  | 8 | 7 | 10 | 6 |  | Blueprint pack | Architecture-grade premium content |  | Backlog
20 | Power Automate | Flow Optimization Engine | Scale | 9 | 10 | 9 | 10 | 3 |  |  |  | 6 | 9 | 10 | 10 |  | SaaS | Potential SaaS with defensible analysis |  | Backlog
21 | Power Automate | Connector and Licensing Finder | MVP | 9 | 8 | 10 | 8 | 8 |  |  |  | 8 | 9 | 8 | 3 |  | Freemium + leads | Reduces discovery and licensing friction |  | Backlog
22 | Power BI | DAX Pattern Library | MVP | 10 | 9 | 10 | 8 | 9 |  |  |  | 9 | 10 | 9 | 2 |  | Freemium | Evergreen SEO and trust engine |  | Backlog
23 | Power BI | DAX Generator | MVP | 10 | 10 | 10 | 8 | 7 |  |  |  | 8 | 10 | 10 | 4 |  | Pro subscription | Large audience and subscription utility |  | Backlog
24 | Power BI | Executive KPI Card Library | MVP | 10 | 9 | 9 | 9 | 8 |  |  |  | 9 | 9 | 9 | 3 |  | Premium pack | Visually marketable and bundle-friendly |  | Backlog
25 | Power BI | PMO Dashboard Pack | MVP | 9 | 10 | 8 | 10 | 7 |  |  |  | 9 | 7 | 10 | 4 |  | Premium pack | Strong founder-market fit and vertical value |  | Backlog
26 | Power BI | Portfolio Management Dashboard Pack | Growth | 9 | 10 | 8 | 10 | 6 |  |  |  | 9 | 7 | 10 | 6 |  | Enterprise pack | Enterprise reporting bundle |  | Backlog
27 | Power BI | Government Reporting Pack | Growth | 8 | 10 | 7 | 10 | 6 |  |  |  | 8 | 6 | 10 | 6 |  | Enterprise pack | Underserved, accessibility-led niche |  | Backlog
28 | Power BI | SVG Visual Library | MVP | 9 | 9 | 9 | 9 | 9 |  |  |  | 9 | 9 | 8 | 2 |  | Freemium + pack | Low effort, high visual and SEO appeal |  | Backlog
29 | Power BI | Theme Generator | MVP | 10 | 8 | 10 | 8 | 8 |  |  |  | 9 | 10 | 8 | 3 |  | Freemium | Lead magnet with repeat usage |  | Backlog
30 | Power BI | Model Health Checker | Scale | 9 | 10 | 9 | 10 | 4 |  |  |  | 7 | 8 | 10 | 9 |  | SaaS | High-value SaaS diagnostic |  | Backlog
31 | Power BI | Measure Documentation Generator | Growth | 9 | 9 | 8 | 9 | 6 |  |  |  | 8 | 8 | 9 | 6 |  | Pro subscription | Saves governance and handover effort |  | Backlog
32 | Architecture | Reference Architecture Library | MVP | 9 | 10 | 9 | 10 | 8 |  |  |  | 9 | 8 | 10 | 3 |  | Freemium + premium blueprints | Primary enterprise differentiation |  | Backlog
33 | Architecture | Solution Blueprint Generator | Growth | 9 | 10 | 8 | 10 | 5 |  |  |  | 7 | 8 | 10 | 8 |  | Pro subscription | Transforms guidance into a product |  | Backlog
34 | Architecture | ALM Strategy Builder | Growth | 9 | 10 | 8 | 10 | 6 |  |  |  | 8 | 7 | 10 | 6 |  | Enterprise license | Enterprise delivery accelerator |  | Backlog
35 | Architecture | Environment Strategy Builder | Growth | 9 | 10 | 8 | 10 | 6 |  |  |  | 8 | 7 | 10 | 6 |  | Enterprise license | Governance-led acquisition |  | Backlog
36 | Architecture | Disaster Recovery Pattern Library | Growth | 8 | 10 | 7 | 10 | 7 |  |  |  | 8 | 6 | 10 | 5 |  | Blueprint pack | High-value mission-critical guidance |  | Backlog
37 | Architecture | Azure Integration Blueprint Pack | Growth | 8 | 10 | 8 | 10 | 6 |  |  |  | 8 | 6 | 10 | 6 |  | Premium pack | Architect and consultant appeal |  | Backlog
38 | Architecture | Fabric Integration Blueprint Pack | Growth | 9 | 10 | 9 | 9 | 6 |  |  |  | 7 | 8 | 10 | 7 |  | Premium pack | Expanding cross-platform demand |  | Backlog
39 | Governance | Governance Template Library | MVP | 9 | 9 | 9 | 10 | 9 |  |  |  | 9 | 8 | 9 | 2 |  | Freemium + pack | Fast-to-build authority content |  | Backlog
40 | Governance | Governance Health Assessment | Growth | 9 | 10 | 9 | 10 | 6 |  |  |  | 8 | 8 | 10 | 7 |  | SaaS + consulting | Lead generation plus SaaS path |  | Backlog
41 | Governance | DLP Policy Design Assistant | Growth | 9 | 10 | 9 | 10 | 5 |  |  |  | 7 | 7 | 10 | 8 |  | Enterprise subscription | High enterprise pain and risk sensitivity |  | Backlog
42 | Governance | Naming Convention Generator | MVP | 8 | 7 | 9 | 8 | 10 |  |  |  | 9 | 8 | 7 | 1 |  | Free | Fast SEO tool and lead magnet |  | Backlog
43 | Governance | Solution Documentation Generator | Growth | 10 | 10 | 9 | 10 | 6 |  |  |  | 8 | 9 | 10 | 7 |  | Pro subscription | Broad pain with strong willingness to pay |  | Backlog
44 | Governance | Tenant Analytics Suite | Scale | 9 | 10 | 8 | 10 | 3 |  |  |  | 6 | 8 | 10 | 10 |  | Enterprise SaaS | High ARR potential, integration-heavy |  | Backlog
45 | Governance | Environment Cost Analyzer | Scale | 8 | 10 | 9 | 10 | 4 |  |  |  | 6 | 7 | 10 | 9 |  | Enterprise SaaS | FinOps angle and executive value |  | Backlog
46 | AI | Prompt Library for Makers | MVP | 10 | 7 | 10 | 7 | 10 |  |  |  | 8 | 10 | 7 | 1 |  | Freemium | Rapid content acquisition and SEO |  | Backlog
47 | AI | AI Solution Architect Advisor | Scale | 10 | 10 | 9 | 10 | 3 |  |  |  | 6 | 9 | 10 | 10 |  | SaaS | Flagship differentiator, high complexity |  | Backlog
48 | AI | RAG Pattern Library | Growth | 9 | 9 | 9 | 9 | 7 |  |  |  | 7 | 8 | 9 | 5 |  | Premium blueprints | Emerging architecture demand |  | Backlog
49 | AI | Agent Template Marketplace | Growth | 9 | 9 | 9 | 9 | 5 |  |  |  | 7 | 8 | 9 | 8 |  | Marketplace commission | Emerging marketplace category |  | Backlog
50 | AI | AI Builder Recipe Library | MVP | 8 | 8 | 9 | 8 | 9 |  |  |  | 8 | 8 | 8 | 2 |  | Freemium + pack | Accessible path for citizen developers |  | Backlog
51 | Developer Tools | Dataverse Schema Designer | Growth | 9 | 10 | 9 | 10 | 5 |  |  |  | 8 | 8 | 10 | 8 |  | Pro subscription | High-value architecture utility |  | Backlog
52 | Developer Tools | Dataverse Schema Analyzer | Scale | 9 | 10 | 8 | 10 | 4 |  |  |  | 7 | 7 | 10 | 9 |  | SaaS | SaaS diagnostic and consulting lead |  | Backlog
53 | Developer Tools | Solution Estimator | Growth | 8 | 10 | 9 | 9 | 7 |  |  |  | 8 | 7 | 9 | 5 |  | Pro + consulting | Consultant-friendly planning tool |  | Backlog
54 | Developer Tools | Architecture Diagram Generator | Growth | 9 | 9 | 9 | 10 | 5 |  |  |  | 7 | 8 | 9 | 8 |  | Pro subscription | Strong shareability and subscription value |  | Backlog
55 | Developer Tools | Power Apps Performance Scanner | Scale | 9 | 10 | 9 | 10 | 3 |  |  |  | 6 | 8 | 10 | 10 |  | SaaS | Difficult but defensible SaaS |  | Backlog
56 | Community | Project Showcase Gallery | Growth | 8 | 7 | 9 | 9 | 7 |  |  |  | 8 | 8 | 8 | 5 |  | Sponsorship + Pro profiles | Social proof, backlinks and creator acquisition |  | Backlog
57 | Community | Design Challenges | Growth | 8 | 6 | 9 | 9 | 7 |  |  |  | 7 | 8 | 8 | 5 |  | Sponsorship | Recurring engagement loop |  | Backlog
58 | Community | Structured Learning Paths | Growth | 9 | 8 | 10 | 8 | 6 |  |  |  | 8 | 9 | 9 | 7 |  | Subscription | SEO depth and subscription retention |  | Backlog
59 | Community | Community Forum and Q&A | Scale | 8 | 6 | 9 | 7 | 4 |  |  |  | 7 | 9 | 8 | 9 |  | Ads + subscription | Network effects but moderation-heavy |  | Backlog
60 | Marketplace | Creator Marketplace Platform | Scale | 9 | 10 | 9 | 10 | 3 |  |  |  | 7 | 9 | 10 | 10 |  | Commission + subscription | Long-term network-effect moat |  | Backlog

## Scoring Weights
WEIGHTED SCORING MODEL
Criterion | Weight | Scoring guidance | Direction
Market Demand | 30% | 1 = niche/uncertain; 10 = broad, recurring pain | Higher is better
Revenue Potential | 25% | 1 = weak willingness to pay; 10 = strong recurring/enterprise value | Higher is better
SEO Value | 15% | 1 = little search intent; 10 = broad evergreen search demand | Higher is better
Competitive Differentiation | 20% | 1 = commodity; 10 = clear defensible advantage | Higher is better
Effort Efficiency | 10% | 1 = very costly/slow; 10 = fast and inexpensive | Higher is better
Total
Decision thresholds
Tier 1: Build Now | 85
Tier 2: Next | 78
Tier 3: Later | 70
Tier 4: Explore | 0
How the score works
Weighted Score = SUM(each 1-10 score × its weight) × 10. Change blue cells to run scenarios.

## Roadmap View
ROADMAP & PORTFOLIO VIEW
Headline metrics
Total features |  | Tier 1 candidates |  | MVP candidates |  | Average weighted score
Phase summary |  |  |  |  | Category portfolio
Phase | Feature Count | Average Score | Suggested focus |  | Category | Count | Average Score
MVP |  |  | Acquisition wedge and first revenue |  | AI
Growth |  |  | Enterprise depth and retention |  | Architecture
Scale |  |  | Defensible SaaS and network effects |  | Community
Developer Tools
Governance
Marketplace
Power Apps
Power Automate
Power BI

## Instructions
HOW TO USE THIS WORKBOOK
1. Adjust weights | On Scoring Weights, edit the blue percentages. Keep the total at 100%.
2. Score features | On Feature Matrix, edit blue 1–10 input cells. Effort Efficiency is inverse, so 10 means fast/easy.
3. Compare outputs | Weighted Score, Rank, Priority Tier, and RICE Score update automatically.
4. Plan delivery | Use Target Phase, Owner, Status, and Notes to convert prioritization into an active backlog.
5. Filter decisions | Filter by Category, Tier, Phase, business model, owner, or status.
6. Revisit monthly | Update confidence and input scores as customer interviews, analytics, and sales evidence accumulate.
Scoring interpretation
9–10 | Exceptional / clear evidence
7–8 | Strong
5–6 | Moderate / validate
3–4 | Weak
1–2 | Very weak / speculative
Important note | Initial scores are strategic assumptions from the feature matrix. Replace them with evidence from interviews, search demand, conversion tests, and sales discovery.